## Open
WDCO Board Action Tracker
Item/Action | Date Added | Issue | Assignee | Estimated Completion Date | Assignee Comments/response: Updated June Board | Assignee Comments/response: Update July Board | Assignee Comments/response: Update September Board | Assignee Comments/response: Update October Board | Assignee Comments/response: Update November Board | Assignee Comments/response: Update December Board | Assignee Comments/response: January update | Assignee Comments/response: February update | Assignee Comments/response: March update | Assignee Comments/response: April update | Assignee Comments/response: May update | Assignee Comments/response: June update | Assignee Comments/response: July update | Assignee Comments/response: September update | Assignee Comments/response: October update | Assignee Comments/response: November update | Assignee Comments/response: December update | Assignee Comments/response: January update | Assignee Comments/response: February update | Assignee Comments/response: March update | Assignee Comments/response: April update | Assignee Comments/response: May update | OPEN
Cllr Sarah Young has contacted Streetscene, they have not carried out a risk assessment on the issue of windows. She has replied and has asked them why they haven’t and if they intend to. Cllr Sarah Young to report back to Board on Members Enquiry regarding health and safety of windows. +6:6 21st March Action Sarah and Tom will follow up with Trevor regarding this matter. | May Board 22 | The windows in Residence Tower | BH | June 22 Board | Cllr Sarah Young had contacted Streetscene again regarding the pavement area under the Residence Tower and was awaiting their reply. | Still waiting response, will continue to chase. | will chase up | Cllr to ciculate LBH reply | Cllr Sarah Young will provide an update once LBH Health and Safety have received report from BH. This hasn’t been received as yet. | Cllr Sarah Young has advised there is no update, LBH Health and Safety Team are still waiting for a report from Berkeley Homes. | Hackney have asked for the action to be assigned to BH. Berkeley is currently not in a position to issue the report, however, Trevor Hughes confirmed that as soon as they are able to issue the report and the finding they will share it with Hackney. | Berkeley is currently not in a position to issue the report, however, as soon as they are able to issue the report and the finding they will share it with Hackney. | Berkeley is currently not in a position to issue the report to Hackney on the windows in Residence Tower | Berkeley is currently not in a position to issue the report, the letter issued back in November is still relevant. |  | The majority of the interim remedial work to the previously locked off windows is complete. There is one window outstanding, which has been subject to a delay because of the limited availability of the access equipment. We hope to have this resolved within the next 2 weeks. We can confirm that all KSS1 apartments will be attended to by a specialist contractor in due course for further enhancements to be made to the windows. We are finalising with our consultant what those enhancements will consist of, which has involved primary and subsidiary testing, with an expectation that all work to enhance the windows can be completed in one visit. We will provide a further update on this once we have finalised the scope of work with our consultant. Trevor has also asked BH Group Legal representative if they can advise on when this report will/may be available. | The update remains consistent with the one provided during the June Board meeting. | Trevor confirmed at the Liaison meeting that the update on the windows report remains unchanged, with Berkeley not yet in a position to share the report. | The update statement from BH Group Legal is included in the latest WDCO Board report as “The interim remedial work to the previously locked off KSS1 windows is complete insofar as possible. A further update will be provided once we have our consultant’s advice on any other recommended measures to further enhance the performance, operation and use of the KSS1 windows.” | The update statement from BH Group Legal is included in the latest WDCO Board report as “The interim remedial work to the previously locked off KSS1 windows is complete insofar as possible. A further update will be provided once we have our consultant’s advice on any other recommended measures to further enhance the performance, operation and use of the KSS1 windows. |  | Berkley confirmed that the update on the windows report remains unchanged, with Berkeley not yet in a position to share the report. | The interim remedial work to the previously locked off KSS1 windows is complete insofar as possible. A further update will be provided once we have our consultant’s advice on any other recommended measures to further enhance the performance, operation and use of the KSS1 windows | Update on the windows report remains unchanged | Jaime advised that Trevor provided an update at the Liaison meeting. Roda will circulate the update once the minutes are finalised. | Update from the April Liaison meeting: Trevor mentioned the pending update regarding the window report from the specialist consultant and their group legal. He anticipated progress on this matter during the week, particularly focusing on a remedial strategy agreement for entering the apartments in KSS1 1 for any necessary improvement works. He reiterated his commitment to sharing updates as soon as they are available. Update from the May Liasion meeting: Trevor reported at the Liasion meeting that the report is now with their group legal and they are reviewing it. | Pending
Anthony will arrange a meeting with Omar will be meeting to discuss the Birchwood 2020/21 accounts. 21st March Action: Roda will follow up with Omar to determine if the action can be closed. | November Board 23 | Service charge | NHG | [18 empty] | JG sent more detailed service charge update to WDCO, ITLA, Councillors etc. on 15.01.24 (this email update includes more info than is included in the WDCO board report. | James Glass (Director of Places & Estates) has spoken to Omar on the phone twice in recent weeks to dicsuss service charge progress and other subjects. | James has spoken to Omar and he has been provided with all the service charges updates Jada sent out to WDCO, ITLA, Cllr, etc. | Omar has requested that the Board hold off on closing the action. He has been trying to contact James to obtain an update on the service charges and to establish a timeframe for when the service charge refund will be provided. | Update from the Liaison meeting on 7th May: Anthony stated that an update on the timeframe for publishing the 20/21, 21/22, and 22/23 accounts will be provided in two weeks. | Open
Hilary brought attention to the ongoing review of the feasibility study prepared by Arup, seeking clarification on when it will be accessible to the District Heat Network working group. 15th February Action: Hermione will take this back to Isobel. | January Board 24 | DHN | LBH | 15th February | [18 empty] | The Council is still reviewing the draft feasibility study prepared by Arup. An update will be brought to the DHN Working Group as soon as possible. | Isobel, are looking to convene a woking group meeting. A summary and and update on the | Expedition are reviewing key documents, including the energy strategy for the masterplan and the Arup feasibility study, in order to present this back to the DHN Working Group. A date has not yet been agreed for this meeting, but will be scheduled to take place in the next few weeks. |  | Open
Hackney will providing an update on the out-of-phase split household in their Board report, which should include a timeframe for when the policy will be implemented. | February Board 24 | LLP | LBH | March Board | [19 empty] | Isobel provided an update on split households: there are ongoing discussions within the Council about the approach towards implementing the policy, considering the significant number of families interested in split household moves and the limited availability of void properties to facilitate these moves. Hackney is intending to provide a more detailed update at a future Board meeting. | Senior officers in the Benefits and Homeless Preventation Service, Regeneration and Housing are working through the ramifications of a split households policy on the demand for homes to meet homelessness and severe overcrowding and are in the process of working up a number of options that might meet the ambitions of WDCO going forward. This policy work is underway and advanced however, the options are still being worked on and have not been presented to elected Members yet. It is hoped that at the WDCO meeting scheduled for July the draft report will be available to be tabled for discussion subject to the approval of the Chair. | Update at the Liasion meeting was that the draft report is scheduled for the July Board | Open
The partners will arrange for the Service Charge Working Group to reconvene to discuss Phase 3 and the management of the social rented blocks. | March Board 24 | Service charge | BH, LBH and NHG | April Board | [21 empty] | Update from the Liaison meeting on 7th May: NHG is awaiting the budget from R&R for Phase 3 before scheduling the service charge working group meeting. | Open
Note on Y5: Microsoft Office User: RH will follow up with Omar to confirm whether the action can be closed.

## Closed Actions
WDCO Board Action Tracker Closed Actions
Item/Action | Date Added | Issue | Assignee | Estimated Completion Date | Assignee Comments/response: Updated June Board | Assignee Comments/response: Update July Board | Assignee Comments/response: Update September Board | Assignee Comments/response: Update October Board | Assignee Comments/response: Update November Board | Assignee Comments/response: Update December Board | Assignee Comments/response: January Update | Assignee Comments/response: February Update | Assignee Comments/response: March Update | Assignee Comments/response: April Update | Assignee Comments/response: May Update | Assignee Comments/response: June Update | Assignee Comments/response: July Update | Assignee Comments/response: Sep Update | Assignee Comments/response: Oct Update | Assignee Comments/response: November Update | Assignee Comments/response: December Update | Assignee Comments/response: January Update | Assignee Comments/response:FebruaryUpdate | Assignee Comments/response: March Update |  | STATUS
Berkeley Homes will ensure the local labour percentage is included in future reports. | May 22 Board | BH report | BH | June 22 Board | Percentage in June Report | Percentage in July Report | Percentage is in the September report | Agreed to Close | [17 empty] | Closed
Hackney to feedback on young persons access to the West Reservoir. | May 22 Board | West Reservior Access | LBH | June 22 Board | GLL have done quite a lot of work in the past to promote the Reservoir and its activities to residents of WD via WDCO, attendance at various events, open days and also running sessions with the Edge Youth Club. In addition, they already run many school sessions, a weekly youth club on multiple days during the week during the summer (https://www.better.org.uk/leisure-centre/London/hackney/west-reservoir-centre/youth-club-stoke-newington-west-reservoir-centre) and holiday programmes (https://www.better.org.uk/leisure-centre/london/hackney/west-reservoir-centre/multi-activity-stoke-newington-west-reservoir-centre). | [20 empty] | Closed
ITLA to consider ways to encourage greater attendance at the face to face board meetings | June Board | Board meetings | ITLA |  | ITLA have reviewed the option of facilitating hybrid Board meetings, to allow for Board members to attended virtually. Unfortunately, the Redmond Centre doesn't have the equipment to allow us to conduct hybrid meetings and the acoustics are not great in the main hall. We will look at other alternatives. | Reviewed the hybrid meeting option for Redmond Centre and no change in availability. Main hall isn't suitable for face to face meetings, MHDT don’t have sufficient equipment for rooms 1 &2. Contacted Berkeley Homes regarding the equipment they use, large meetimng room in BHs phse 3 site office is cramped and need to exit at 7pm as security leave. Vision suite in marketing is similarly cramped for face ti face and IT equipment isnt working. |  | ITLA contacted MHDT regarding capacity on hybrid meetinsg and the Partner Presentation on Phase 4 was hybrid following provision of new IT equipment by BHs to MHDT. Can Board members and partners that used zoom to attend that meeting please give feedback in how well it worked? | Feedback from the hybrid partners presentation suggested that it was difficult hear the discussion and those who attended on zoom couldn’t participate. | [16 empty] | Closed
ITLA to email LBH about the reopening of the regeneration office. | June Board | Reopening of the Office | ITLA/LBH | July Board |  | Jane has discussed this with Head of Leasehold services, they will need to coordinat this with NHG. Hackney is carrying out a borough wide consulation in autum. | Verbal update will be provided at September Board | LBH regeneration report back to future board on plans and hours of opening of Woodberry Down Office. | The office is now open to the public between 9am - 12 o’clock on Monday, Wednesday and Friday each week. | [16 empty] | Closed
Board agreed to set up a Constitution Working Party made up of 6 Board Members. ITLA to bring back to Board in July for final places to be filled. | June Board | Constitutional working group | ITLA | July Board |  | This is on the agenda for the July Board meeting | This is on the agenda for the September AGM | AGM appointed reps, ITLA to set up first meeting. | First meeting was held on 3rd November | Adrian asked for written responses from Board members on how the constitution might be changed. | [15 empty] | Closed
ITLA to share Resident Association details across resident associations so they can make their own liaison arrangements. | July Board | Resident Associations | ITLA | September Board |  |  | ITLA has emailed individuals from the Residents Association and requested authorisation to share their contact details. | Completed | [17 empty] | Closed
ITLA to send email to LBH regarding the involvement process of the West Reservoir Advisory Board, including WDCO reps, in the scoping stage of the appointed Design Team. Cllr to contact Parks regarding desire for co-production approach to West Reservoir project. | October Board | West Reservoir Advisory Board | ITLA/Cllr | [5 empty] | Email from Ian Holland has advised that the vite visit was a familiarisation visit for the design team and outlining to them the key areas of the site that will be the focus for the project. They will set out the parameters for the project at the first Board meeting. | [16 empty] | Closed
ITLA will invite Rico Prince to the next Board meeting. | November Board | Invite to Board meetings | ITLA | [6 empty] | ITLA has invited Rico and he will be attending the December Board | [15 empty] | Closed
Neil Coles and Local Management (NHG) to meet Chair of Maplewood TRA regarding rodent infestation. | October Board |  | NHG | [6 empty] | Meeting was held on 6th December | [15 empty] | Closed
NHG meet with Rendall and Ritner regarding approach to dealing with rodents. | October Board | Pest control | NHG | [6 empty] | Meeting is scheduled for Wednesday 13th December | [15 empty] | Closed
LBH to update Board on outcome of Freedom of Information request on Housing Needs survey | September Board | What information in housing needs survey can be shared and what is confidential | LBH | October |  |  |  | LBH have not been able to identify the Freedom of Information request referred to by Elaine Gosnell at last Board. | ITLA have emailed Elaine for the reference number. |  | FOI requests details of the number of tenants who chose to move off the estate rather than move into the kick start sites or the Phase 2. | [14 empty] | Closed
ITLA to email Berkeley Homes on the issue of the failure of the window in Residence Tower and the continuing sewage problems in Woodberry Grove North. | July Board | The windows in Residence Tower | ITLA | September Board |  |  | ITLA email BH regarding this. | NHG to continue to update Board on sewage issue and look to provide final findings and lessons learnt with WGN residents and WDCO Board. | NHG Head of Compliance is attending the November board to answer questions on Sewage issue in WGN. | NHG have provided an update in the Board report on sewage issue | NHG have provided an update in the Board report on sewage issue | [14 empty] | Closed
Jaime Powell will endeavour to get a prompt response from Berkeley Homes senior management. | July Board | The windows in Residence Tower | BH report | September Board |  |  | Formal update to WDCO will be released on Thursday the 15th of September. | Jaime to take back WDCO an Cllr concerns on reasons for window failure, if other phases used same window and query on current compliance of that style of windows in high blocks to BHs HQ for response. | Berkeley Homes confirming that the windows that failed on KSS1 were only used on that phase and were compliant for the types of buildings they were used on | BH legal team have sent the Board a letter responding to their requests | BH have issued an update on the windows in their report and they have not had any response to the letters sent to WDCO and LBH from our Legal Team | ITLA has circulated copy of the letter on 13th and 20th January. | [13 empty] | Closed
ITLA will request that reps are included in the drafting of the Landscaping Task and Finish group ToR. | November Board | Landscaping Task and Finish group | ITLA | [6 empty] | A programme of meetings will be set up for the new year where the Terms of Reference will be developed and a schedule of tasks identified. | Board will appoint reps in February. | Board appointed Jackie, Hilary and Philip. | [13 empty] | Closed
Samuel Betts (NHG) will check with Rendall and Ritner to see if their issue with pest control was linked to the jetting. | November Board | WGN sewerage system | NHG | [6 empty] | Samuel Betts took away the action to see if lessons could be learned from R&R’s recent drainage jetting which preceded rodent infestation issues. R+R have responded to say they are unfamiliar with the link but if more details can be provided regarding when this occurred and any particular addresses this relates to then then can investigate further. The ITLA has emailed Eleanor and asked if she could provide more information. | ITLA have emailed Eleanor: "R&R have asked if more details can be provided regarding when this occurred and any particular addresses this relates to so they can investigate this further. Are you able to provide further information?" | Samuel Betts confirmed he spoke to R&R but, to the best of their knowledge, none of their jetting works caused any rodent infestations. Eleanor clarified that the issue wasn’t in relation to the sewage. | [13 empty] | Closed
Berkeley Homes will be sharing the Masterplan engagement strategy at the February Board. | January Board | Masterplan | BH | February Board | [7 empty] | The engagement and ground floor strategies were shared with the Board. | [13 empty] | Closed
Roda will circulate the presentation from Thames Water and any further comms. | January Board | Presentation | ITLA | January | [7 empty] | Presentation was circulated on 20th Jan | [13 empty] | Closed
Roda will request for rodents/pest control strategy to be an item for the next SMB meeting in February. | January Board | Rodents | ITLA | February | [8 empty] | Rodents/pest control strategy is on the agenda for the SMB meeting on 16th March | [12 empty] | Closed
NHG will provide the update regarding the service charge review request to the Maplewood & Birchwood Resident Association. | January Board | Service charge | NHG | February | [8 empty] | NHG will review the 22/23 accounts before the final accounts go out to all residents in September 2023. As part of this process, they will also review the 20/21 accounts for all the blocks which includes social rented. | [12 empty] | Closed
ITLA and BH to invite Rendall and Ritner to Board meetings. | November Board | R&R | BH and ITLA | [6 empty] | ITLA has emailed BH and asked them to invite R&R to the December Board. ITLA has also sent the Board papers to Elisa Keating and Emily Sheppard from R&R. | BH have invited R&R to future Board meetings. |  | R&R will be attending the February Board | [12 empty] | Closed
Roda will continue to liaise with Eleanor on the issue at Parkway. | February Board | Rodents/pest control | ITLA | [9 empty] | Eleanor has confirmed that this has been resolved | [12 empty] | Closed
Partners will send their answers to the written question to ITLA. Roda will circulate answers to the written questions. | February Board | Written Question | MHDT/BH/LBH/ITLA | March | [8 empty] | Completed 3rd March | [12 empty] | Closed
Hackney will provide an update at the March Board meeting. | February Board | SSR | LBH | March Board | [8 empty] | Update provided in the March report. | [12 empty] | Closed
Roda will summarise the outcome of the discussion and will share it with the Board to approve. | February Board | Community cohesion | ITLA | 20th February | [8 empty] | Completed | [12 empty] | Closed
Roda will email PC Zaka the dates of the Board. Roda will circulate details for the upcoming CAP meeting. | March Board | CAP meetings | ITLA | [10 empty] | Completed CAP meeting hasn't been arranged but ITLA will circulated once meeting details had been provided. | [11 empty] | Closed
Roda and Jane will contact Hermione regarding updating the Board members on Block D. | March Board | Block D | LBH and ITLA | [10 empty] | Update sent to working group members on the 3rd April. Further update included in the Hackney report | [11 empty] | Closed
Jane will check what the lease stipulates in terms of when Block D should be in operation by. | March Board | Block D | LBH | [10 empty] | No requirement in the headlease but something to protect against unnecessary vacancy etc will be included in the sub-lease with MillCo. Intention is that MillCo occupy as soon as possible. | [11 empty] | Closed
Roda will provide the Board with all of the constituencies that have vacant positions so that Board members can think about how to approach bi- elections. | March Board | Bi-elctions | ITLA | [10 empty] | Completed | [11 empty] | Closed
Roda will send an invite to all Board members to Tuesday’s Executive Committee meeting. | March Board | Executive Committee meeting | ITLA | [10 empty] | Completed | [11 empty] | Closed
LBH to discuss with partners issues around affordability of heating and Heat Network Working Group to report back to September Board. 16th March: Jane Havemann will chase this with Nicola Hudson to get dates in the diary for the DHN meetings. | July Board | Heat Network Working Group | LBH | September Board |  |  | The next residents newsletter will detail available support for residents facing high energy bills. The DHN working group will meet in October and report back to the November Board | NHG to bring rep to Board to answer questions and concerns on billing and heating charges for NHG blocks. | NHG arranged a meeting on 7th November with the WDCO reps from the NHG block to discuss the heating charges and ineffective heat meters. The notes/comments from that meetings have been included in the NHG WDCO Update Report | The DHN working group will meet in the new year | The working group will be invited to a series of workshops in the New Year to review the Community Interest Company (CIC) ownership and operation model in light of the current energycrisis. | Expedition has now been appointed so the District Heating Network meetings will commence shortly. |  | First meeting scheduled for the 4th May | [11 empty] | Closed
Council Decant Team to provide timetable update on implementation of split household element of Local Lettings Policy. | June Board | Local Lettings Policy | LBH |  |  | Colin has suggested that they will be contacting tenant in later phases to identify the number of residents that wish to do a split household. |  |  | Hackney will provide a verbal update regarding the Local Lettings Policy at November Board | Hackney will provide a verbal update regarding the Local Lettings Policy at the December Board | First priority for split households is Phase 4. Colin Bright to prepare a programme for split households in phases 5-8. | There is a central list of all households who have indicated interest in split household. A total of 9 cases have been approved for split household in Phase 4 and the checks and verification process will be completed in February. They are anticipating starting viewings for some of the split households in March. There are currently 12 households who have indicated interest in split household in Phase 5. Letters were sent to residents in Phases 6, 7 and 8 and there were 43 responses across all three phases. The Decant team and the ITLA will begin to hold drop-in sessions for split households in Phases 6-8 to discuss residents’ rehousing requirements. They are anticipating this to start in March, and the verification process letters will be sent out afterwards. | Colin will attend March WDCO to answer question. The Council will be reviewing the LLP in spring with James Goddard. | As discussed at the March Board a review will be carried out in April. Will report back on progress of the review in May. | [11 empty] | Closed
Jane Havemann will speak to Hackney Head of Maintenance regarding damp and mould, she will report back. 19th Jan - Jane will provide an update on the timescale. | November Board | Damp and mould | LBH | [6 empty] | Information on the incidence of damp and mould cases on Woodberry Down Estate is being collated and analysed in conjunction with Housing Services to determine the extent of the issue in the older blocks on the Estate, and how to manage this going forward. | The Regeneration team and Head of Housing Services are looking at a strategic approach for surveying older parts of the estate that are part of the masterplan. | Find attached update form Hackney | A verbal update was provided at the February Board on damp and mould; a written update was subsequently circulated on the 6th March by the ITLA. | Will continue to provide updates in the Hackney Board report | [11 empty] | Closed
Neil Coils will check if they can provide this within two months and will update Omar next week. | April 23 Board | Service charge | NHG | 28th April | [10 empty] | Jada confirmed that the Birchwood accounts for 2020-21 will be reviewed by end of June 2023. | [10 empty] | Closed
Neil Coils will check if Hackney Environmental Health have been notified. | April 23 Board | WGN sewerage system | NHG | May Board | [10 empty] | Jada confirms that previous overflows were reported to LBH Environmental Health at the time. Please note there has not been an overflow for a prolonged period. | [10 empty] | Closed
Roda will email MHDT and ask if the percentage of utilisation of the Redmond Centre can be included in their report to the Board each month | April 23 Board | Redmond Centre | ITLA/MHDT | May Board | [10 empty] | Update provided in the May report | [10 empty] | Closed
ITLA will invite Simon Donovan to the May Board. | April 23 Board | MHDT | ITLA/MHDT | May Board | [10 empty] | Simon Donovan will be attending the May Board | [10 empty] | Closed
Roda will send an email to Board members who did not attend the April Board inquire about their interest in becoming a representative on the District Heat Network (DHN) working group. | April 23 Board | DHN | ITLA | May Board | [10 empty] | Roda emailed Board members who didn't attend the last meeting | [10 empty] | Closed
Roda will send an email on when Kalu will be able to share the budget reconciliation. | April 23 Board | WDCO budget reconciliation | ITLA | May Board | [10 empty] | Finaance Committee meeting is tentatively scheduled for 31st May 6.30pm on zoom, awaiting confirmation. | [10 empty] | Closed
Roda will come back with the dates to hold the bi-elections. | April 23 Board | Bi-elections | ITLA | May Board | [10 empty] | See attached | [10 empty] | Closed
Roda will circulate the CAP meeting details to the Board upon receiving the date from the Police. | April 23 Board | CAP meeting | ITLA | May | [10 empty] | The next Woodberry Down Ward CAP meeting is scheduled for 25/05/23. | [10 empty] | Closed
Samehra Arif will ensure an update and estimated completion time is provided for the Rowan Apartments gate. | March 23 Board | M&E | NHG | 24th April | [9 empty] | NHG confirmed the estimated completion date for the gate is Monday 24th April. | Issues with Rowan pedestrian gate and intercom now resolved. | [10 empty] | Closed
Tom will check if the Church was contacted as part of the religious groups and will report back. | May 23 Board | Masterplan Engagement | BH | June Board | [11 empty] | Comm Comm have reported that they contacted St Olaves in 2021 as part of the earlier Masterplan consultation, however, St Olaves didn’t want to be consulted then or in the future, so they weren’t contacted this time round. | [9 empty] | Closed
A synopsis of the project will be sent to Roda to circulate. | May 23 Board | My Place Project | MHDT | June Board | [11 empty] | Circulated by ITLA on 14th June | [9 empty] | Closed
Simon Donovan will provide the Board with an update on the use of the centre and financial information to run the centre. | May 23 Board | Redmond Contre | MHDT | June Board | [11 empty] | Circulated by ITLA on 15th June | [9 empty] | Closed
NHG will share the outcome from the WGN investigation/report on the sewerage system. 16th Feb - WDCO would like to see the reports on the sewerage system to fully understand the cause of the problem. 15th June: Samuel Betts assured the Board that he would personally communicate with Tracy Lavers to ascertain when NHG would be able to share the reports with WDCO. | November 22 Board | WGN sewerage system | NHG | May Board | [5 empty] | ITLA emailed Neil Coils on 3rd Jan for an update | Update provide in the Board report. NHG are now looking at the best approach to facilitate the installation of the new pumps and new macerator. | NHG not in a position to share the report yet, there have been subsequent reports and best course of action we believe is to complete the works and combine the reports. | NHG will be providing report at the May Board | Neil Coils confirmed that Samuel Betts will be attending the June Board to provide the update on WGN and the outcome of the sewage. | Along with our papers for the June board, we will provide a summary report on the sewage system and the works we’ve done to correct the problems. As before, Sam Betts will attend to run through this and answer any questions. | Sam Betts will attend the board to provide a summary on the works we have completed to correct the problems and confirm timeframe for the completion of the replacement macerator and pump set. He will answer any questions related to this. | D&L reports/results of the works and surveys carried out by our contractor D&L were shared wth Roda and Cllr by email on 17 July 2023. Once all the remedial work has been completed we will share a final a summary. | Completed | [7 empty] | Closed
The Board has requested for LBH to provide an update on what actions are being taken for the identified cases of damp and mould. 18th May: LBH will provide the data on the damp and mould at June Board. 18th May: LBH Building Maintenance will be attending the June Board to provide an update on where they are with the damp and mould cases 15th June: Carol will provide the more refined data with Phase breakdown by the Liaison meeting for Roda to circulate to the Board. 15th June: Roda will circulate figures/update from Hackney to the Board after the operational meeting on Thursday 29th June. 15th June: Loulla Weeks will be attending the Hackney Operational meeting at the end of June and provide figures. | April 23 Board | Damp and mould | LBH | May Board | [10 empty] | Housing Services are preparing an update on progress made to date on properties that have had damp and mould issues, which can be provided at the Board in May. | "Housing Services are preparing an update on progress made to date on properties that have had damp and mould issues and an officer from the Building Maintenance team will provide an update at the June Board. " | Hackney clarified that this information was received on Thursday 20th July. Isobel and Carol will review the data and subsequently distribute it. | Information was provided in August to Roda. Any further operational queries regarding damp and mould can be picked up on a quarterly basis at the LBH Operations meeting. | [7 empty] | Closed
Samuel will take note of the concerns and ensure that an update regarding the gates issue is provided at the NHG Contracts meeting. | June 23 Board | M&E | NHG | [13 empty] | JG provided an update on gates at the Operational Meeting with WDCO and the ITLA on 11 July 2023. The Estate Team are meeting with Sam Betts and Andy Lord (Head of Compliance) to discuss M&E related issues on WD on 25 July 2023. | [8 empty] | Closed
If the Board has any questions regarding the reports from their sewage contractor DNL, Roda will forward them to NHG. | July Board 23 | WGN sewerage system | ITLA | [14 empty] | No questions were received by ITLA from the Board members. | [7 empty] | Closed
Roda will share the Phase 4 presentation with the Board members. Board members will forward additional questions regarding the last few slides of the presentation to Roda, who will then circulate them to Berkeley. | July Board 23 | Phase 4 | ITLA | [14 empty] | ITLA circulated the presentation on 13th September | [7 empty] | Closed
Roda will distribute any further inquiries from the Board regarding the Block D update members to Hermione. | July Board 23 | Block D | ITLA | [14 empty] | No additional questions were received by ITLA from the Board members. | [7 empty] | Closed
Simon Donovan will share the Hidden River Festival budget with Roda who will circulate it to the Board. | July Board 23 | Hidden River Fest | MHDT | [14 empty] | Information was circulated on 24th August | [7 empty] | Closed
Roda will forward the local talent launch information from Simon Donovan to the Board. | July Board 23 | Hidden River Fest | MHDT | [14 empty] | Information not received. Simon Donovan was uncertainty regarding the action about the local talent launch. | [7 empty] | Closed
Simon Donovan will provide information on stalls and charity groups to Roda, who will circulate it to the Board. | September Board 23 | HRF | MHDT | [22 empty] | Closed
Roda will chase this with Hackney. | September Board 23 | WDCO Budget | ITLA | October | [14 empty] | Budget has been approved by Hackney | [6 empty] | Closed
The Chair will follow up with Deputy Mayor Guy Nicholson to check progress with the actions from the meeting. | October Board 2023 | Masterplan | WDCO Chair | November 23 Board | [18 empty] | Completed |  |  | Closed
The Chair will email the Board’s request to the partners on Monday. | October Board 2023 | Board presentations | WDCO Chair | 23rd October 23 | [18 empty] | Completed |  |  | Closed
Roda will add the acceptance of the September minutes on the agenda for the November Board. | October Board 2023 | Board minutes | ITLA | November 23 Board | [18 empty] | Completed |  |  | Closed
Anthony will find out the timeline for when Birchwood residents entitled to a refund will receive a surplus payment from NHG and will provide this information to the Board members. | October Board 2023 | Service Charge | NHG | November 23 Board | [18 empty] | The Estate Team will now benefit from a dedicated Service Charge Business Partner within NHG Places, who will assist us in completing the review as soon as possible. We can provide a new timeline once we have met with w/c 20 Nov to discuss. |  |  | Closed
Jaime has confirmed that these aspects will be incorporated into the November presentation. | October Board 2023 | Masterplan: Section 13 of the Hackney Plan regarding parking | BH | November 23 Board | [18 empty] | To be provided at the November Board |  |  | Closed
Anthony will take the issues on the emergency lighting and fobs back to NHG and will come back with an update | October Board 2023 | M&E | NHG | November 23 Board | [18 empty] | On-site ECG engineer carries out regular emergency lightning tests. Jada recently shared our ECG compliance tracker with WDCO and Roda which lists this and how frequently. |  |  | Closed
NHG will arrange a meeting with WDCO members from the NHG blocks to discuss how they can achieve the objectives and improve estate inspections and walkabouts. | October Board 2023 | Estate Walkabout | NHG | November 23 Board | [18 empty] | Roda updated that at the NHG Operations meeting discussed, NHG agreed to reinstate the walkabouts until M&E issues are resolved. WDCO representatives expressed satisfaction, considering the matter resolved. |  |  | Closed
1. Tom will come back with answers regarding the car parking and cycle parking podiums in conjunction with the ground floor presentation. 2. Tom will provide a response along with examples of active and non-active podiums during the ground floor strategy presentation. | September Board 23 | Masterplan | BH | November 23 Board | [18 empty] | To be provided at the November Board |  |  | Closed
Tom will clarify Section 13 of the Hackney Plan with Hackney’s Transport Officers. | Nov Board 23 | Masterplan | BH | [18 empty] | In the writen update | Update provided in January |  |  | Closed
Jaime will provide an answer at the next Liaison meeting regarding the feasibility of including buyer demographic information in the Berkeley report. 16th November: Berkeley to provide information by the next Liaison meeting ahead of December Board. | October Board 2023 | Demographics of buyers | BH | 5th December | [15 empty] | Tom reported that Jaime is currently on leave but assured that he will address this matter and provide an update. |  |  | The demographic sales data was shared with the Board on 6th February. |  |  | Closed
WDCO asked Berkeley to provide an explanation on how the viability is assessed long-term. 1. ACTION: Tom will take this back and provide a clarification at the October or November Board. 2. ACTION: Berkeley will also provide an explanation on why there is a requirement for an increase at the November Board. | September Board 23 | Masterplan | BH | November 23 Board | [15 empty] | To be provided at the January Board | To be provided at the January Board | To be provided at the January Board | Completed in January |  |  | Closed
Hackney Regen team will also come back with information about the viability in November. | September Board 23 | Masterplan | LBH | November 23 Board | [14 empty] | Hackney Regen team are in the process of working on the viability information for the November board. | To be provided at the January Board | To be provided at the January Board | To be provided at the January Board | Completed in January |  |  | Closed
Anthony will distribute the presentation ahead of the Board, allowing Board members to review it in advance. The presentation will then be summarised for a shorter update at the December Board meeting. | October Board 2023 | Masterplan: Affordability presentation | NHG | November 23 Board | [15 empty] | Meeting be provided at the December Board | The affordability presentation will be delivered at the January or February Board. | The Intermediate Housing presentation is scheduled to be delivered at the Design Committee on 31st January. Once it has been presented to the Design Committee, it will come to the Board in February. | On the agenda for February Board |  |  | Closed
Jaime and Anthony will raise this concern with Trevor, work together to find a solution, and present an update at the upcoming Liaison meeting. 16th November: Tom to address William's concern regarding reception in Rowan and Hornbeam with Trevor. 18th January: NHG will look into this and confirm who will be responsible for installing a Freesat box. | October Board 2023 | TV aerials | NHG & BH | 7th November 23 | [15 empty] | BH commissioned an independent Survey on the TV reception at Rowen & Hornbeam. This occurred on the 20th of September and has been shared with NHG. The outcome statement was “Overall – the system has been well installed - No fault has been found by TV AV Installations Engineers on 20th September 2023 – Amp levels were high but wouldn’t have cause many issues - They had spoken to tenants & been able access a few flats – All are saying the problem was there about 3 weeks ago – It is all been fine for last couple of weeks”. BH are not aware of any further issues. |  | NHG confirmed in an email to WDCO, ITLA etc on 06.12.23 that our contractor had attended on 31.10.23 and confirmed the follwing: "Tested the main head-end and found satellite reception was working fine but the terrestrial signal from Crystal palace is very poor. Accessed the roof, new build construction has been built taller which is now affecting line of sight to CP TV transmitter even more so that previously. We have previously installed a secondary aerial to receive reception from the Ally Pally TV transmitter which means the reception is working fine on the main public service broadcast but the commercial broadcasts are only available from CP. Don't think we can guarantee a good reception from CP anymore due to the line of sight issues, residents can still receive the public service broadcasts from Ally pally or can switch to FreeSat services instead to receive free TV services. To install a taller mast on this roof would be challenging due to not having any structure to fit brackets too etc. Client needs to provide more information and rise individual jobs specific for each resident if they have no reception at all as that is not a communal issue. If the residents report that they are missing and/or some channels are breaking up on Freeview then this is due to the communal issue as mentioned but as we have not been provided with any residents to refer to I could not confirm this on today’s visit. System tested and working barring the issues with reception problems on the commercial Freeview broadcasts." As advised we will continue to raise individual jobs if a resident has no signal at all but they may need to switch to Freesat services. We will ask the advice of our colleagues in the M&E team re options to install a taller mast on the roof as the contractor has stated this will be challenging and there is no guarantee it will improve things. | NHG have provided Billy with a free sat box to trial for a period. JG and MM have attended his proeprty to try and set up however it requires another cable. We will order this however we will not send out an engineer as this is not a repair. Once it has been trialled we will feedback. |  |  | Closed
Adrian will chase this up with Michael Pamment and will update the Board. | Nov Board 23 | Insite Billing | WDCO | [17 empty] | Adrian reported to the Board the outcome of his discussions regarding historic heating charges, namely that that Berkeley have now capped their charges and will withdraw the reclaims. Adrian gave credit to the work of the Residents Association, including Oonagh, who established that the legal basis for the charges was inappropriate. | Action completed | Completed in January |  |  | Closed
Roda will confirm with the Hackney Planning Officer when Phase 4 is scheduled to go to the planning sub-committee. | 2024-01-01 | Phase 4 | ITLA | 24th January | [18 empty] | Roda emailed the Board on 23rd January and advised that Phase 4 application is currently scheduled for the March Planning Sub-Committee, which is scheduled for Wednesday 6th March. |  |  | Closed
Isobel Pierce will take this away and come back to WDCO. | June 23 Board | Rodents/pest control strategy | LBH | [14 empty] | The Council is in the process of co-ordinating the next meeting. | Hackney Regen team are in the process of organising another meeting with the appropriate personnel from each organisation. |  |  | In progress - a meeting will be arranged with the Vermin Group. | In progress - a meeting will be arranged with the Vermin Group. |  |  | Closed
Chair's follow-up with Deputy Mayor Guy Nicholson awaits response. Isobel to send a reminder to Deputy Mayor Guy Nicholson | Nov Board 23 | Masterplan | LBH | [18 empty] | Chair's follow-up with Deputy Mayor Guy Nicholson awaits response. | A response will be provided wk/c 19th February | Update and a response tomorrow |  | Closed
The ITLA will provide the figures regarding the approval rate of the second masterplan. | February Board | Masterplan | ITLA | [20 empty] | Completed |  | Closed
Roda will circulate the amended motion, which was passed by the Board, to all members for their reference. Roda will send the motion to the Hackney Planning Officer. | February Board | Phase 4 | ITLA | [20 empty] | Completed |  | Closed
Executive Committee need to agree a date for the community forum 20.04. 23: Roda will check if the Executives would like to present the proposed amendment in May. 15th June: Mina, Omar and Geoff are looking to meet after the Board and will report the next steps back to the Board. 15th June: They will also look at what areas the questionnaire should focus on. 20th July: : Mina, Geoff and Omar will update at the AGM. 19th October: Roda will schedule a meeting for Omar, Mina, and Geoff to continue planning for the Public Forum. 21st March Action: Roda will look into getting a microphone for the event. | May 22 Board | Community Forum | WDCO Board | 2023-07-01 | Date for Community Forum to be discussed at the Executive meeting on 21 June | The Executive Committee have recommended holding the Public/Community Forum between the end of November beginning of December before the design committee commences discussion on the masterplan. The Executive Committee have also highlighted a number of questions around the logistics of the meeting and would like to discuss with the Board the logistics and recommends setting up a working group or arrange a series of meetings to plan the Public Forum event. |  |  |  | At the November board, there was a discussion about holding the Community Forum, Geoff highlighted that it is vital to organise this before any consideration and discussion of the Masterplan. Board members felt it would be beneficial to discuss this further and understand what WDCO want to achieve from the forum and how they intend to use the information. It was also noted that it is important to understand what the constraints are and comprehend the brief of the masterplan before considering holding a forum. |  | On the agenda for February Board. | There was not sufficient time to discuss the community/public forum. The Board has agreed to have it on the agenda for the March Board. | As discussed at the March Board, a resolution was passed in December 2021 in which the Board made a commitment to hold a community forum in regards to the new masterplan. Although, the resolution did not specify when the Community forum should be held, it was agreed at the March Board that we currently do not have the capacity to hold the Community Forum. The Executive have therefore proposed that the resolution is amended. | Geoff, Omar, and Mina volunteered to develop a proposal for the Public Forum and present it to the Board | Geoff, Omar, and Mina volunteered to develop a proposal for the Public Forum and present it to the Board in June. ITLA circulated notes from the first meeting. | The Public forum group has not met since the June Board and are scheduled to meet next week. | Geoff reported that no movement or progress has been made regarding the Public Forum, as they were waiting for the Design Committee to make progress on the Masterplan review. |  | Geoff, Mina and Omar are due to meet next week. |  |  |  | The Community Forum was held on 11th April | The Community Forum was held on 11th April | Close
Hackney will present the housing number at the March Board. | 2024-02-01 | Masterplan | LBH | March Board | [19 empty] | Hackney will present the housing numbers at the April Board meeting. The figures are currently undergoing internal review, and they are awaiting final approval before being presented to the Board. | The full response will be brought to WDCO at the next meeting scheduled for May 16th subject to the approval of the Chair | Close
Cllr Nicholson will arrange a meeting separately with Mina and Elaine to discuss their individual case regarding the out-of-phase split household. | 2024-03-01 | LLP | Cllr | April Board | [20 empty] | Cllr Nicholson to follow up directly to the residents involved. | Close
Isobel will follow this up with Library services and will provide an update. | 2024-03-01 | Library | LBH | 2nd April | [20 empty] | The library services team have increased availability of staff at the WD library. There will be an external book depository at Stoke Newington Library and there are additional activities taking place at both Stamford Hill Library and in Clissold House, for example rhymetime sessions. Residents are welcome to email the library service team directly for more updates at ourlibraries@hackney.gov.uk. | Close
Roda will email Clare to inquire about the Design Committee Masterplan workshops and when the outcome of the Public Consultation will be discussed with the Design Committee. | 2024-03-01 | Masterplan | ITLA | April Board | [20 empty] | Completed- workshop has been arranged for Wednesday 1st May | Closed
Tom will verify whether the information regarding the committee report will be uploaded as per each comment or summarised. | 2024-03-01 | Planning | BH | April Board | [21 empty] | Close